## Build Checklist
Respond.io SaaS Clone — Master Build Checklist v3.0
n8n embedded as headless workflow engine ¦ 4 Phases ¦ 52 Tasks ¦ Updated March 2026
# | Phase | Type | Task | Details / Acceptance Criteria | Depends On | Key Decisions / Notes | Est. Days | Status
1 | Phase 1 | devops | Provision cloud infrastructure | 3-node K3s cluster (or VPS fleet). PostgreSQL 16, Redis 7, S3-compatible storage. NATS JetStream. Traefik ingress with auto-TLS. | — | DECISION: AWS EKS vs Hetzner K3s vs self-hosted. K3s recommended for cost phase. | 3
2 | Phase 1 | security | TLS, firewall & network hardening | Cloudflare WAF + DDoS in front. Traefik TLS termination with Let's Encrypt. Firewall rules: deny all inbound except 80/443. Internal services communicate over private network only. | #1 | Must complete BEFORE any external service connections (WhatsApp webhooks, etc.) | 2
3 | Phase 1 | infra | PostgreSQL RLS tenant isolation | Implement Row-Level Security policies on all tables. Every table has tenant_id column. RLS enforced at DB level, not just application. Test: cross-tenant query returns 0 rows. | #1 | Chatwoot uses Account model — extend with RLS policies on top | 3
4 | Phase 1 | infra | Deploy NATS JetStream event bus | Install NATS with JetStream enabled. Create core streams: conversation.*, message.*, contact.*, billing.*. Define event envelope schema (event_type, tenant_id, correlation_id, timestamp, payload). Test: publish event → consumer receives within 100ms. | #1 | NATS is the central nervous system. All cross-service communication flows through it. | 2
5 | Phase 1 | devops | CI/CD pipeline setup | GitHub Actions: lint → test → build container → push to registry → ArgoCD deploy. Branch strategy: main (prod), develop (staging), feature/*. Automated test gate on PR merge. | #1 | Establish BEFORE any feature development begins | 2
6 | Phase 1 | build | Fork Chatwoot & rebrand | Fork chatwoot/chatwoot repo. Strip branding (logo, colors, copy). Establish clean fork boundary: customizations in separate modules/plugins where possible. Upstream tracking branch for security patches. | #5 | DO NOT modify Chatwoot core files unless absolutely necessary. Extend via plugins/hooks. | 3
7 | Phase 1 | build | Extend contact model — lifecycle pipeline | Add lifecycle_stage field to Contact model (configurable stages: New Lead → Qualified → Customer → Churned). Stage transitions emit contact.lifecycle_changed events to NATS. UI: Kanban view of contacts by stage. | #6, #4 | Respond.io's 'Lifecycle Management' is a key differentiator vs vanilla Chatwoot | 4
8 | Phase 1 | build | Inbox enhancements — SLA timers & collision detection | Add per-conversation SLA timer (configurable per workspace). Escalation trigger when SLA breached → emits event → can trigger workflow. Typing indicator collision detection (agent A sees 'Agent B is typing'). | #6 | SLA timers are Growth+ feature but build the infrastructure now | 3
9 | Phase 1 | build | Web chat widget deployment | Deploy Chatwoot SDK web widget. Customizable appearance (colors, position, greeting). Visitor identification via email/phone. Pre-chat form support. | #6 | This is the easiest channel and validates the full message pipeline end-to-end | 2
10 | Phase 1 | integration | Apply for WhatsApp BSP access (360dialog + Twilio) | Submit BSP applications to BOTH 360dialog and Twilio in parallel. Complete Meta Business verification. Prepare test phone number. Expected approval: 2-4 weeks. | — | START THIS WEEK 1. Longest lead-time item. Blocks production WhatsApp. | 1
11 | Phase 1 | integration | WhatsApp Business API integration | Implement WhatsApp channel adapter: receive_message() → NormalizedMessage, send_message() → WhatsApp API call. Webhook receiver with Meta signature verification. Message templates with variable interpolation. Delivery/read receipt handling. | #6, #10 (approval) | Use Evolution API for dev/testing while waiting for BSP approval. NEVER in production. | 5
12 | Phase 1 | integration | Additional channel adapters (Telegram, Email, SMS) | Telegram Bot API adapter. Email (IMAP/SMTP) adapter. SMS via Vonage/Twilio adapter. All conform to same channel adapter interface. | #6 | Telegram is fastest to integrate (no approval process). Good for early demos. | 4
13 | Phase 1 | devops | Monitoring stack: Grafana + Prometheus + Loki | Deploy Grafana, Prometheus, Loki. Instrument Chatwoot with Prometheus metrics. Log aggregation from all services. Dashboard: request latency, error rates, active connections, queue depths. | #1 | OpenTelemetry tracing added in Phase 2 when multi-service architecture kicks in | 2
14 | Phase 1 | billing | Stripe Billing integration — Starter tier | Stripe Checkout for signup. Subscription management (Starter plan: $79/mo, 5 users). User seat add-on ($12/mo per additional user). Webhook handler for payment events (invoice.paid, subscription.updated, etc.). | #3 | Stripe is the billing backbone. Get this right early — revenue depends on it. | 4
15 | Phase 1 | build | Tenant onboarding flow | Self-service signup: email → verify → create Account → provision workspace → connect first channel wizard. Stripe checkout integrated into signup. Welcome email with getting-started guide. | #6, #14 | This IS the product experience. Smooth onboarding = conversion. | 3
16 | Phase 1 | build | Mobile app fork (React Native) | Fork Chatwoot mobile app. Rebrand. Deploy to TestFlight (iOS) and Play Console (Android) for beta testing. Core features: inbox view, conversation reply, notifications. | #6 | Mobile is table-stakes for respond.io competitors. Ship beta quality in Phase 1. | 4
17 | Phase 1 | security | Phase 1 security audit | Penetration test on exposed endpoints. Verify RLS isolation (cross-tenant probe). Check webhook signature verification. Review API auth flow. Dependency vulnerability scan. | #1-#16 | Gate before accepting paying customers | 2
18 | Phase 2 | infra | Deploy n8n as headless workflow engine | Deploy n8n in Docker/K8s. Disable public UI (headless mode). Configure REST API access with API key auth. Set up PostgreSQL as n8n's backend DB (separate schema from main app). Configure webhook receiver endpoint. | #1, #4 | n8n runs as INTERNAL service only. Customers never see n8n UI — they use our React Flow builder. | 3
19 | Phase 2 | build | Workflow graph translator (React Flow → n8n JSON) | Build translation layer: our React Flow graph JSON → n8n workflow JSON format. Map our node types (trigger, condition, action, AI step) to n8n node equivalents. Support: If/Else, Wait, HTTP Request, Set Variable, Switch, Merge nodes. | #18 | This is the critical bridge. Our UI speaks React Flow; n8n speaks its own JSON schema. | 5
20 | Phase 2 | build | React Flow visual workflow builder UI | Drag-and-drop workflow builder using React Flow. Node palette: Triggers (new conversation, keyword match, contact field changed, scheduled, webhook). Conditions (if/else, time gate, A/B split). Actions (send message, update contact, assign agent, HTTP webhook, delay). AI Steps (AI Respond, AI Classify, AI Extract). | #18 | Users design workflows here. Backend translates to n8n JSON and pushes via API. | 8
21 | Phase 2 | integration | NATS → n8n trigger bridge | Build a bridge service that subscribes to NATS event streams and triggers n8n workflows via webhook. Event mapping: conversation.created → 'New Conversation' trigger, message.inbound with keyword → 'Keyword Match' trigger, contact.field_updated → 'Contact Updated' trigger, scheduled events via cron. | #4, #18 | This connects the event bus to the workflow engine. Every trigger type needs a NATS → n8n webhook mapping. | 3
22 | Phase 2 | integration | n8n → platform action endpoints | Build REST API endpoints that n8n action nodes call back into: POST /api/v1/actions/send-message, POST /api/v1/actions/update-contact, POST /api/v1/actions/assign-agent, POST /api/v1/actions/add-tag, POST /api/v1/actions/change-lifecycle, POST /api/v1/actions/close-conversation. Each endpoint validates tenant context and emits NATS events. | #4, #18 | These are the 'effector' endpoints. n8n workflows call these to take actions in the platform. | 4
23 | Phase 2 | build | Workflow versioning & management | Version each published workflow (immutable snapshots). Active executions continue on their version. New triggers use latest published version. Rollback UI. Execution history with per-step status and timing. | #19, #20 | n8n has built-in execution history — expose it through our API | 3
24 | Phase 2 | build | Broadcast engine | Audience segmentation builder (contact fields + lifecycle + tags → dynamic segments). WhatsApp template selection with variable interpolation. Scheduling (immediate, scheduled, timezone-aware). Throttling respecting WhatsApp tier limits (80 msgs/sec). Cost estimation before send. | #11, #7 | Broadcasts are a major revenue driver — they demonstrate immediate ROI to customers. | 6
25 | Phase 2 | build | Broadcast analytics | Per-broadcast dashboard: sent, delivered, read, replied, failed. Per-message delivery status tracking. Cost per broadcast (WhatsApp conversation charges). Export to CSV. | #24 | Analytics close the loop — customers need to see broadcast ROI | 3
26 | Phase 2 | infra | pgvector + pg_trgm setup for hybrid search | Install pgvector extension in PostgreSQL. Create knowledge_chunks table with vector column (1536 dimensions for text-embedding-3-small). Build HNSW index for sub-100ms retrieval. Install pg_trgm for BM25 keyword matching. Test: hybrid query returns relevant chunks within 100ms. | #3 | This MUST be done before the ingestion pipeline. Vector store is the foundation of RAG. | 2
27 | Phase 2 | ai | Knowledge base ingestion pipeline | Ingest sources: PDF (layout-aware via unstructured.io), DOCX, URL (crawl with boilerplate stripping), plain text, images (OCR). Semantic chunking at ~512 tokens with 50-token overlap. Embed via text-embedding-3-small (or equivalent via LiteLLM). Upsert to pgvector. Metadata per chunk: source, section, date. Re-index on document update. | #26 | Quality of RAG depends entirely on chunking quality. Layout-aware PDF chunking is critical. | 6
28 | Phase 2 | ai | LiteLLM provider abstraction layer | Deploy LiteLLM as unified LLM gateway. Configure providers: OpenAI (GPT-4o, GPT-4o-mini), Anthropic (Claude Sonnet, Haiku), Ollama (local models). Model selection configurable per-tenant and per-agent. Smart routing: simple intents → cheap models, complex → frontier models. | #1 | LiteLLM is already in your MBS stack — reuse that expertise. | 2
29 | Phase 2 | ai | AI Orchestrator — multi-agent architecture | Build orchestrator that routes messages to micro-agents: Retrieval Agent (RAG), Action Agent (CRM updates, HTTP requests, workflow triggers), Routing Agent (human handoff logic), Response Agent (final customer-facing message with guardrails). Confidence scoring on every response. | #27, #28 | This is the respond.io 'AI Orchestrator' pattern. NOT a single monolithic agent. | 8
30 | Phase 2 | ai | AI agent templates (Sales, Support, Receptionist) | Pre-built agent configurations: AI Sales Agent (lead qualification, product recs, appointment booking). AI Support Agent (FAQ, ticket creation, escalation). AI Receptionist (greeting, intent routing, info collection). Custom Agent builder with configurable knowledge, actions, guardrails. | #29 | Templates dramatically reduce time-to-value for new customers. | 4
31 | Phase 2 | ai | AI Assist features (agent-facing) | In-conversation AI tools for human agents: Response drafting (suggest reply based on context). Tone adjustment (formal ↔ casual). Translation (auto-detect language, translate). Summarization (conversation summary for handoff). These use the same LiteLLM layer. | #28 | Lower priority than customer-facing AI agents but high perceived value. | 3
32 | Phase 2 | ai | AI sandbox testing environment | Safe environment to test AI agents before production: Simulated customer conversations. Per-step visibility (retrieved chunks, confidence, response). Guardrail verification. No impact on live conversations. | #29, #30 | Respond.io has this. Critical for enterprise customer confidence. | 3
33 | Phase 2 | infra | ClickHouse analytics pipeline | Deploy ClickHouse. Build ETL pipeline: NATS events → ClickHouse materialized views. Core metrics: response times, resolution times, agent workload, channel volumes, conversation outcomes. Grafana dashboards for internal + customer-facing reports. | #4 | ClickHouse handles the analytics workload without degrading the primary PostgreSQL. | 4
34 | Phase 2 | build | Advanced reporting dashboards | Customer-facing analytics: Response time by agent/team. Channel performance comparison. Broadcast ROI. AI agent resolution rate + confidence distribution. Conversation outcome tracking. Export to CSV/PDF. | #33 | Growth+ tier feature. Analytics drive expansion revenue. | 4
35 | Phase 2 | billing | MAC metering & Growth tier billing | Redis HyperLogLog counters for unique MAC tracking per billing period. Real-time usage dashboard (current MAC vs. limit). Threshold alerts (80%, 90%, 100%). Overage billing at end of cycle ($12/100 MACs). Stripe metered billing integration. Growth plan: $159/mo, 10 users, AI + workflows + broadcasts. | #14, #4 | Metering is non-negotiable for the MAC pricing model. HyperLogLog gives <1% error at minimal memory. | 4
36 | Phase 2 | integration | Zapier/Make webhook integration | Expose inbound webhook endpoint (receive triggers from Zapier/Make). Expose outbound webhook events (conversation.*, contact.*, message.* → Zapier/Make). Standard Zapier app definition with auth, triggers, and actions. | #4, #22 | Zapier/Make integration unlocks the long-tail of CRM/tool connections. | 3
37 | Phase 2 | security | Phase 2 security audit + AI safety review | Full security audit on new services. AI-specific: prompt injection testing, PII leakage testing, guardrail bypass attempts. Token budget enforcement verification. Cross-tenant AI isolation (Tenant A's knowledge not accessible to Tenant B). | #18-#36 | AI introduces new attack surfaces. Dedicated review is essential. | 3
38 | Phase 3 | integration | HubSpot bi-directional CRM sync | Contact sync: platform ↔ HubSpot (create, update, merge). Conversation sync: log conversations as HubSpot activities. Deal/pipeline sync: lifecycle stage → HubSpot deal stage. Conflict resolution: last-write-wins with configurable priority. Rate limit handling with exponential backoff. | #7 | CRM sync is the #1 enterprise requirement. HubSpot first (largest market share in target segment). | 6
39 | Phase 3 | integration | Salesforce bi-directional CRM sync | Same sync patterns as HubSpot adapted to Salesforce APIs. Contact/Lead/Opportunity mapping. Salesforce Connected App OAuth flow. Bulk API for large-scale sync operations. | #38 | Reuse patterns from HubSpot integration. Salesforce is harder (SOAP legacy, field mappings). | 5
40 | Phase 3 | integration | WhatsApp Business Calling API | Enable voice calls within WhatsApp conversations. Inbound call handling → route to agent or AI. Outbound calls with consent flow. Call recording + transcription. Call activity in same conversation thread. Call metrics: duration, outcome, wait time. | #11 | Respond.io launched this globally. Must have for feature parity. | 6
41 | Phase 3 | integration | VoIP integration (Telnyx) | Connect Telnyx SIP trunk for traditional phone calls. Inbound/outbound calling from inbox. Call recording + transcription. Number provisioning (buy numbers via Telnyx API). Call transfer between agents. | #1 | Complements WhatsApp Calling — reaches non-WhatsApp customers. | 5
42 | Phase 3 | build | Multi-workspace support | Account can contain multiple Workspaces (Advanced+ plan). Each workspace: independent inboxes, agents, workflows, AI agents. Shared: billing, owner analytics. Cross-workspace reporting for account owners. | #3, #14 | Required for multi-brand/multi-location customers (e.g., car dealership chains). | 5
43 | Phase 3 | security | SSO implementation (SAML 2.0 / OIDC) | Integrate Authentik or Auth0 for enterprise SSO. SAML 2.0 + OIDC support. Per-tenant SSO configuration. Enforce SSO-only login for Advanced+ tenants. Directory sync (Azure AD, Okta, Google Workspace). | #1 | Enterprise gate feature. Leverage your Authentik MBS expertise. | 4
44 | Phase 3 | integration | Meta Product Catalog integration | Connect Meta Commerce catalog. In-chat product browsing (carousel). Product detail sharing. Order placement via messaging. Catalog sync automation. | #11 | High value for retail/e-commerce customers. | 4
45 | Phase 3 | integration | Meta CAPI integration | Conversions API integration for click-to-WhatsApp/Messenger ads. Attribution tracking: ad click → conversation → conversion. Optimize ad targeting based on conversion data sent back to Meta. | #11 | Major respond.io selling point — directly ties ad spend to chat conversions. | 3
46 | Phase 3 | build | HTTP request step in workflows (Advanced tier) | n8n HTTP Request node exposed via our workflow builder. Configurable: URL, method, headers, body, auth. Response mapping to workflow variables. Timeout + retry configuration. | #18, #20 | Gated to Advanced tier. n8n's HTTP Request node handles this natively — just expose in UI. | 2
47 | Phase 3 | billing | Advanced + Enterprise tier billing | Advanced plan: $279/mo, SSO, multi-workspace, HTTP workflows, custom channels. Enterprise: custom pricing, unlimited users, higher API rate limits. Volume discounts. Annual billing with 20% discount. Invoice generation for enterprise. | #35 | Expand Stripe Billing with new plan tiers and enterprise invoicing. | 3
48 | Phase 3 | security | SOC 2 / ISO 27001 audit preparation | Document all security controls. Implement missing controls from audit checklist. Evidence collection automation. Engage audit firm for SOC 2 Type II readiness assessment. | #37 | Start preparation in Phase 3, target certification in Year 2. | 5
49 | Phase 4 | ai | Voice AI Agents | AI-powered inbound call handling via WhatsApp Calling + VoIP. Real-time speech-to-text → AI orchestrator → text-to-speech. Action execution during calls (CRM update, booking, workflow trigger). 3-minute session cap per respond.io pattern. Multilingual (32 languages). | #29, #40, #41 | Respond.io's newest flagship feature. High complexity but major differentiator. | 10
50 | Phase 4 | integration | TikTok DM + Custom Channel API | TikTok DM channel adapter (lead capture from TikTok ads). Custom channel API: generic webhook-based adapter for proprietary messaging systems. Both conform to standard channel adapter interface. | #6 | TikTok is growing fast in respond.io's target markets (SEA, LATAM). | 5
51 | Phase 4 | build | MCP Server for AI tool integration | Build MCP (Model Context Protocol) server enabling external AI tools and automation platforms to connect to the platform without custom connectors. Expose: conversations, contacts, workflows, AI agents via MCP tools. | #22 | Respond.io just launched this. Forward-looking integration pattern. | 4
52 | Phase 4 | build | Developer portal + self-hosted option | API documentation (OpenAPI spec, interactive explorer). SDKs (JavaScript, Python). Webhook builder UI. Self-hosted deployment: Helm charts, docker-compose, documentation. Partner/reseller program infrastructure. | #22 | Developer portal is the enterprise scaling play. Self-hosted unlocks regulated industries. | 8
TOTAL ESTIMATED EFFORT | [6 empty] | 205 | eng-days

## n8n Integration Map
n8n Integration Endpoints — Trigger & Action Mapping
Defines how NATS events trigger n8n workflows and how n8n action nodes call back into the platform
A. NATS Event → n8n Workflow Triggers
NATS Event | n8n Trigger Type | Webhook URL Pattern | Payload Fields | Workflow Builder Label | Notes
conversation.created | Webhook | /webhooks/n8n/{tenant_id}/conversation-created | conversation_id, contact_id, channel_type, inbox_id, initial_message | New Conversation | Fires once per new conversation thread
message.inbound | Webhook | /webhooks/n8n/{tenant_id}/message-inbound | message_id, conversation_id, contact_id, content, channel_type, metadata | Inbound Message | Bridge service filters by keyword match before triggering
message.inbound (keyword) | Webhook (filtered) | /webhooks/n8n/{tenant_id}/keyword-match | message_id, content, matched_keyword, contact_id, conversation_id | Keyword Match | Pre-filtered by bridge service regex/exact match
contact.field_updated | Webhook | /webhooks/n8n/{tenant_id}/contact-updated | contact_id, field_name, old_value, new_value, updated_by | Contact Field Updated | Useful for lifecycle stage change triggers
contact.lifecycle_changed | Webhook | /webhooks/n8n/{tenant_id}/lifecycle-changed | contact_id, old_stage, new_stage, workspace_id | Lifecycle Stage Changed | High-value trigger for sales automation
conversation.assigned | Webhook | /webhooks/n8n/{tenant_id}/conversation-assigned | conversation_id, assignee_id, previous_assignee_id, assignment_method | Conversation Assigned | Fires on manual or auto-assignment
conversation.resolved | Webhook | /webhooks/n8n/{tenant_id}/conversation-resolved | conversation_id, resolved_by, resolution_time_seconds, contact_id | Conversation Resolved | Trigger CSAT survey or follow-up workflows
broadcast.reply | Webhook | /webhooks/n8n/{tenant_id}/broadcast-reply | broadcast_id, contact_id, message_content, conversation_id | Broadcast Reply | Handle responses to bulk broadcasts
ai.handoff_triggered | Webhook | /webhooks/n8n/{tenant_id}/ai-handoff | conversation_id, ai_agent_id, confidence_score, handoff_reason, context_summary | AI Handoff | When AI agent escalates to human — trigger routing workflow
(cron) | Cron Trigger | n8n built-in cron node | N/A — n8n cron triggers execute on schedule | Scheduled | n8n's native cron node. No NATS bridge needed.
(external webhook) | Webhook Trigger | /webhooks/n8n/{tenant_id}/external/{webhook_id} | User-defined payload | External Webhook | Allows customers to trigger workflows from external systems
B. n8n Action Nodes → Platform REST API Endpoints
Endpoint | Method | Request Body | Response | Workflow Builder Label | Notes
/api/v1/actions/send-message | POST | { conversation_id, content, content_type (text/template/media), template_id?, variables?, media_url? } | { message_id, delivery_status } | Send Message | Supports text, templates, and media. Auto-selects channel based on conversation.
/api/v1/actions/update-contact | PATCH | { contact_id, fields: { name?, email?, phone?, lifecycle_stage?, custom_fields?, tags_add?, tags_remove? } } | { contact_id, updated_fields } | Update Contact | Emits contact.field_updated event to NATS
/api/v1/actions/assign-conversation | POST | { conversation_id, assignment_type (agent/team/round-robin/least-busy), target_id? } | { conversation_id, assignee_id } | Assign Agent | Supports all respond.io assignment strategies
/api/v1/actions/add-tag | POST | { entity_type (contact/conversation), entity_id, tags[] } | { entity_id, current_tags[] } | Add Tag | Tags on both contacts and conversations
/api/v1/actions/change-lifecycle | POST | { contact_id, new_stage, reason? } | { contact_id, old_stage, new_stage } | Change Lifecycle Stage | Emits contact.lifecycle_changed → can cascade-trigger other workflows
/api/v1/actions/close-conversation | POST | { conversation_id, resolution_note? } | { conversation_id, status: 'resolved' } | Close Conversation | Marks conversation as resolved. Emits conversation.resolved.
/api/v1/actions/snooze-conversation | POST | { conversation_id, snooze_until (ISO datetime) } | { conversation_id, snoozed_until } | Snooze | Reopens automatically when timer expires
/api/v1/actions/invoke-ai-agent | POST | { conversation_id, ai_agent_id, context? } | { response_text, confidence, actions_taken[] } | AI Respond | Invokes AI orchestrator in context of conversation
/api/v1/actions/ai-classify | POST | { text, categories[], model? } | { category, confidence, reasoning } | AI Classify | Intent/topic classification via LLM
/api/v1/actions/ai-extract | POST | { text, schema: { field_name: type }[], model? } | { extracted_fields: {} } | AI Extract (Objective) | Structured data extraction — respond.io's 'AI Objectives'
/api/v1/actions/create-note | POST | { conversation_id, content, visibility: 'internal' } | { note_id } | Add Internal Note | Visible only to agents, not customers
/api/v1/actions/trigger-webhook | POST | { url, method, headers?, body?, timeout_ms? } | { status_code, response_body } | HTTP Request (Advanced) | Gated to Advanced tier. n8n HTTP Request node wrapper.

## n8n Workflow Examples
n8n Workflow JSON Examples — Common Automation Patterns
Workflow Pattern | Description | n8n Nodes Used | Platform Integration Points
Lead Qualification | New conversation → AI classifies intent → if sales intent: extract contact info → update lifecycle to 'Qualified' → assign to sales team | Webhook Trigger → HTTP Request (AI Classify) → IF node → HTTP Request (AI Extract) → HTTP Request (Update Contact) → HTTP Request (Assign) | Triggers: conversation.created Actions: ai-classify, ai-extract, update-contact, assign-conversation
Auto-Reply + FAQ | Inbound message → AI agent searches knowledge base → if confidence > 0.8: send AI response → else: assign to human agent | Webhook Trigger → HTTP Request (Invoke AI) → IF (confidence check) → HTTP Request (Send Message) OR HTTP Request (Assign) | Triggers: message.inbound Actions: invoke-ai-agent, send-message, assign-conversation
Broadcast Follow-Up | Broadcast reply received → classify reply intent → if positive: create internal note + assign to sales → if negative: send opt-out message | Webhook Trigger → HTTP Request (AI Classify) → Switch node → HTTP Request (Create Note + Assign) OR HTTP Request (Send Message) | Triggers: broadcast.reply Actions: ai-classify, create-note, assign-conversation, send-message
SLA Escalation | Scheduled check (every 5 min) → query conversations with breached SLAs → for each: add 'SLA_BREACH' tag → reassign to manager → send internal alert | Cron Trigger → HTTP Request (query API) → SplitInBatches → HTTP Request (Add Tag) → HTTP Request (Assign) → HTTP Request (Create Note) | Triggers: cron (built-in) Actions: add-tag, assign-conversation, create-note
CRM Sync on Close | Conversation resolved → fetch contact details → push to HubSpot as activity → update HubSpot deal stage if lifecycle = Customer | Webhook Trigger → HTTP Request (get contact) → HubSpot node (create activity) → IF (lifecycle check) → HubSpot node (update deal) | Triggers: conversation.resolved n8n's native HubSpot integration nodes handle CRM calls directly
After-Hours Routing | New conversation → check current time → if outside business hours: send auto-reply + invoke AI agent → if during hours: assign via round-robin | Webhook Trigger → DateTime node → IF node → HTTP Request (Send Message + Invoke AI) OR HTTP Request (Assign round-robin) | Triggers: conversation.created Actions: send-message, invoke-ai-agent, assign-conversation
Multi-Step Onboarding | New contact created → wait 5 min → send welcome message → wait 24h → send product guide → wait 48h → if no reply: send follow-up → assign to agent | Webhook Trigger → Wait (5m) → HTTP Request (Send) → Wait (24h) → HTTP Request (Send) → Wait (48h) → IF (check reply) → HTTP Request (Send/Assign) | Triggers: contact.created Actions: send-message, assign-conversation n8n Wait nodes handle delays natively
AI Handoff Routing | AI agent triggers handoff → extract handoff reason → route to specialist team based on topic → create internal note with AI conversation summary | Webhook Trigger → HTTP Request (get context) → Switch (by topic) → HTTP Request (Assign to team) → HTTP Request (Create Note) | Triggers: ai.handoff_triggered Actions: assign-conversation, create-note

## Phase Summary
Phase Summary — Timeline & Exit Criteria
Phase | Timeline | Task Count | Exit Criteria | Revenue Milestone | Key Risk
Phase 1 | Weeks 1–12 | 17 tasks | Paying customers on Starter tier. WhatsApp + web chat live. Agent inbox fully operational. Mobile app in beta. Stripe billing collecting revenue. | Starter: $79/mo per tenant | WhatsApp BSP approval delay (2-4 weeks)
Phase 2 | Weeks 13–28 | 20 tasks | Growth tier live. Workflows (n8n-powered). AI agents with RAG. Broadcasts with analytics. ClickHouse advanced reporting. MAC metering + overage billing. | Growth: $159/mo per tenant AI + automation = expansion revenue | AI cost per conversation must stay under margin. Smart model routing critical.
Phase 3 | Weeks 29–42 | 11 tasks | Advanced tier live. HubSpot + Salesforce CRM sync. WhatsApp + VoIP calling. Multi-workspace. SSO. Meta CAPI. SOC 2 prep started. | Advanced: $279/mo per tenant Enterprise pipeline building | CRM sync is notoriously brittle. Rate limits, schema mapping, conflict resolution.
Phase 4 | Weeks 43–56 | 4 tasks | Full respond.io feature parity. Voice AI agents. TikTok DM. MCP Server. Developer portal. Self-hosted option. Partner program. | Enterprise: custom pricing Self-hosted: regulated industries | Voice AI is highest complexity. 10 eng-days minimum.